## Sheet1
WBS | Issue Name | Assignee | Labels | Project Phase | Milestone
1.1a | Stakeholder sign-off delayed due to client availability | Thershlin Ramsamy | Schedule | Deliverable 1 – Baseline Project Plan | WP1.1c – Stakeholder Sign-offs
1.1b | Incomplete requirements gathered from initial stakeholder meetings | Thershlin Ramsamy | Planning | Deliverable 1 – Baseline Project Plan | WP1.1a – Gather User Requirements
1.1c | Scope of Work (SOW) needs re-approval after change requests | Thershlin Ramsamy | Change Control | Deliverable 1 – Baseline Project Plan | WP1.1b – Define Scope of Work
1.2a | Missed progress meeting due to resource conflict | Thershlin Ramsamy | Communication | Deliverable 1 – Project Management | WP1.2a – Progress Reports & Team Meetings
1.2b | Delays in updating the issue tracking register | Thershlin Ramsamy | Administrative | Deliverable 1 – Project Management | WP1.2b – Change Control & Issue Tracking
1.3a | Vendor quotations missing during RFQ phase | Jemaine Naidoo | Procurement | Deliverable 1 – Procurement & Contracts | WP1.3a – Vendor Shortlisting & RFQs
1.3b | Contract terms unclear for selected vendor | Jemaine Naidoo | Risk | Deliverable 1 – Procurement & Contracts | WP1.3b – Contract Negotiation
2.1a | UI wireframes lack consistency across screen sizes | Ross Wassenaar | Design | Deliverable 2 – Cross-Platform Mobile App | WP2.1a – Create Wireframes & Style Guide
2.1b | Interactive prototype errors during testing | Ross Wassenaar | Quality | Deliverable 2 – Cross-Platform Mobile App | WP2.1b – Build Interactive Prototypes
2.1c | Usability test feedback not implemented on time | Ross Wassenaar | Schedule | Deliverable 2 – Cross-Platform Mobile App | WP2.1c – Conduct Usability Testing
2.2a | Core feature functionality incomplete due to code merge errors | Yajur Mohan | Technical | Deliverable 2 – Cross-Platform Mobile App | WP2.2a – Implement Core Features
2.2b | Delay in API integration between MVC and Function App | Yajur Mohan | Technical | Deliverable 2 – Cross-Platform Mobile App | WP2.2b – API Integration
2.2c | Device features (camera, GPS) not responding in build | Yajur Mohan | Performance | Deliverable 2 – Cross-Platform Mobile App | WP2.2c – Device Feature Integration
2.2d | Peer code review revealed untested methods | Yajur Mohan | Quality | Deliverable 2 – Cross-Platform Mobile App | WP2.2d – Peer Code Reviews
2.2e | Unit testing delayed due to missing dependencies | Yajur Mohan | Testing | Deliverable 2 – Cross-Platform Mobile App | WP2.2e – Unit Testing & Bug Fixing
2.3a | App performance lag detected on older Android devices | Shuayb Vali | Testing | Deliverable 2 – Cross-Platform Mobile App | WP2.3a – Performance Testing
2.3b | Compatibility issues found on iOS emulator | Shuayb Vali | Quality | Deliverable 2 – Cross-Platform Mobile App | WP2.3b – Cross-Device Compatibility Testing
2.3c | Regression test failed after code merge | Shuayb Vali | Technical | Deliverable 2 – Cross-Platform Mobile App | WP2.3c – Regression Testing
3.1a | Database schema duplication causing data conflicts | Adrian Chetty | Technical | Deliverable 3 – Back-End System & Database | WP3.1a – Design Database Schema
3.1b | API endpoint documentation incomplete | Adrian Chetty | Documentation | Deliverable 3 – Back-End System & Database | WP3.1b – Define API Endpoints
3.1c | Security architecture pending review approval | Adrian Chetty | Risk | Deliverable 3 – Back-End System & Database | WP3.1c – Draft Security Architecture
3.2a | Hosting infrastructure configuration error | Adrian Chetty | Deployment | Deliverable 3 – Back-End System & Database | WP3.2a – Set Up Hosting Infrastructure
3.2b | Function App API returning 500 error during integration | Adrian Chetty | Technical | Deliverable 3 – Back-End System & Database | WP3.2b – Develop API Endpoints
3.2c | Integration between backend and mobile app incomplete | Adrian Chetty | Integration | Deliverable 3 – Back-End System & Database | WP3.2c – Integration with Mobile App
3.2d | Timeout errors during load testing | Adrian Chetty | Performance | Deliverable 3 – Back-End System & Database | WP3.2d – Server Load Testing
3.2e | Minor bugs remaining after testing cycle | Adrian Chetty | Quality | Deliverable 3 – Back-End System & Database | WP3.2e – Bug Fixes & Adjustments
3.3a | Penetration testing delayed due to unavailable tester | Wabo Chetty | Risk | Deliverable 3 – Back-End System & Database | WP3.3a – Penetration Testing
3.3b | Security compliance report not submitted on time | Wabo Chetty | Compliance | Deliverable 3 – Back-End System & Database | WP3.3b – Security Hardening & Compliance
3.3c | CI/CD deployment script build failed | Wabo Chetty | Technical | Deliverable 3 – Back-End System & Database | WP3.3c – CI/CD Deployment Scripts
4.1a | Pilot participants requested testing extension | Jemaine Naidoo | Schedule | Deliverable 4 – Pilot Deployment & Evaluation | WP4.1a – Recruit Pilot Participants
4.1b | App crashes during pilot deployment | Jemaine Naidoo | Technical | Deliverable 4 – Pilot Deployment & Evaluation | WP4.1b – Deploy App to Pilot Devices
4.1c | Slow response from pilot helpdesk | Jemaine Naidoo | Support | Deliverable 4 – Pilot Deployment & Evaluation | WP4.1c – Provide Pilot Support
4.2a | Limited feedback from pilot participants | Muhammed Safwaan | Quality | Deliverable 4 – Pilot Deployment & Evaluation | WP4.2a – Collect Pilot Feedback & Logs
4.2b | Performance analysis delayed | Muhammed Safwaan | Schedule | Deliverable 4 – Pilot Deployment & Evaluation | WP4.2b – Analyse Performance & UX Metrics
4.2c | Final evaluation report missing visuals | Muhammed Safwaan | Documentation | Deliverable 4 – Pilot Deployment & Evaluation | WP4.2c – Compile Evaluation Report
5.1a | User manual draft missing screenshots | Muhammed Safwaan | Documentation | Deliverable 5 – User Documentation & Training | WP5.1a – Draft Full User Manual
5.1b | Quick-start guide missing sections | Muhammed Safwaan | Quality | Deliverable 5 – User Documentation & Training | WP5.1b – Develop Quick-Start Guides
5.1c | Translation of user manuals behind schedule | Muhammed Safwaan | Schedule | Deliverable 5 – User Documentation & Training | WP5.1c – Translate / Adapt Content
5.2a | Low attendance during live training sessions | Shuayb Vali | Schedule | Deliverable 5 – User Documentation & Training | WP5.2a – Conduct Live Training Sessions
5.2b | Training videos need re-recording due to poor audio | Shuayb Vali | Quality | Deliverable 5 – User Documentation & Training | WP5.2b – Create Training Videos
5.2c | Handover package missing installation files | Shuayb Vali | Technical | Deliverable 5 – User Documentation & Training | WP5.2c – Deliver Handover Package